## Sheet1
Task | Owner | Priority | Deadline | Status
Setup GitHub repo & environment | You | High | Day 1 | Not Started
Bootstrap FastAPI backend & health endpoint | You | High | Day 2 | Not Started
Implement Smartsheet OAuth2 login/callback/profile | You | High | Day 3 | Not Started
Bootstrap React/Next.js frontend with login button | You | High | Day 4 | Not Started
Backend: Excel Parsing / Preview endpoint | You | High | Day 5 | Not Started
Backend: Hierarchy Builder service | You | High | Day 6 | Not Started
Frontend: Upload Form + Rule Dropdown | You | High | Day 7 | Not Started
Frontend: Preview Tree UI | You | High | Day 8 | Not Started
Backend: Fetch Smartsheet sheets | You | High | Day 9 | Not Started
Backend: Import Commit endpoint | You | High | Day 10 | Not Started
Frontend: Import Button functionality | You | High | Day 11 | Not Started
Deploy Backend | You | Medium | Day 12 | Not Started
Deploy Frontend | You | Medium | Day 12 | Not Started
Optional: Stripe Integration / Billing | You | Medium | Day 13 | Not Started
Landing page + marketing | You | Medium | Day 14 | Not Started
Beta outreach & user onboarding | You | Medium | Day 14 | Not Started
Iteration / Bug fixes / Feedback | You | High | Day 15+ | Not Started